## Outputs
No. of prisoners | 1440 | Input figure here
Required GIFA | 56706
Calculated Total GIFA ÷ Millsike Density
No. of Houseblocks req'd | 6
Calculated Total GIFA ÷ Millsike Density
Buildings | GIFA
ERH (core) | 3059
ERH (offices) | 200
ERH (visits hall) | 1400
Support | 770
Central services (core) | 3130
Central services (education) | 1500
Central services (gym) | 300
Kitchen | 1926
Workshop | 7257
CASU | 648
Houseblock | 30430
OPU | 6086
Required Acres | 51.0618
Calculated Total GIFA ÷ Millsike Density
Start on site | Q3 (2026) | Choose start on site period
Programme (wks) | 154
Houseblock Duration + ((Number of Blocks - 1) × 4 Weeks) + Commissioning
Description | Cost / m2
Demo | 0
Substructure | 30945982.7948
Superstructure Env | 111051172.662
Superstructure Sub | 29514290.284
Finishes | 25628937.9706
Fittings | 8450973.5969
M&E | 175825289.3135
External works | 132275564.5305
TOTAL | 513692211.1524

## Calculation
Prisoners (Total) | 1440
Prisoners (per HB) | 240
GIFA | 56706
Site area | 143.5
Area / prisoner | 39.3792
Programme (HBs) | 122
Programme (Stagger) | 4
Programme (Commissioning) | 12
Building | GIFA | Status | m2 / person | Notes
ERH (core) | 3059 | Fixed
ERH (offices) | 200 |  | 0.13889
ERH (visits hall) | 1400 |  | 0.97222
Support | 770 | Fixed
Central services (core) | 3130 | Fixed
Central services (education) | 1500 |  | 1.0417
Central services (gym) | 300 |  | 0.20833
Kitchen | 1926 | Fixed
Workshop | 7257 |  | 1200 | per additional HB
CASU | 648 | Fixed |  | 1 additional CASU per 6 HBs
Houseblock | 6086 | Fixed
OPU | 6086 | Fixed |  | 1 additional OPU per 6 HBs
Description | Cost / m2 | Notes
Profit | 119.35 | Mark to transition costs to rows 34 to 42
Central OH | 313.72 | Mark to transition costs to rows 34 to 43
Site OH A | 438.59 | Mark to transition costs to rows 34 to 44
Site OH B | 494.42 | Mark to transition costs to rows 34 to 45
Risk | 143.34 | Mark to transition costs to rows 34 to 46
Specialist fees | 31.41 | Mark to transition costs to rows 34 to 47
Precon fees | 21.18 | Mark to transition costs to rows 34 to 48
Regulatory fees |  | Mark to transition costs to rows 34 to 49
Demo
Substructure | 395.77
Superstructure Env | 1420.24
Superstructure Sub | 377.46
Finishes | 327.77
Fittings | 108.08
M&E | 2248.64
External works | 1691.68
Abnormal, Site Influences & Specific Requirements
Minor works | -118.84
| 8012.81 | 454374403.86
1443.17
6569.64
On cost factor | 1.2197
Date | Quarterly indices adjustment | Adjustment factor
Q1 (2023) | 379 | 0.98956
Q2 (2023) | 383 | 1 | Benchmark data point (midway through HMP M)
Q3 (2023) | 386 | 1.0078
Q4 (2023) | 388 | 1.0131
Q1 (2024) | 390 | 1.0183
Q2 (2024) | 392 | 1.0235
Q3 (2024) | 394 | 1.0287
Q4 (2024) | 397 | 1.0366
Q1 (2025) | 399 | 1.0418
Q2 (2025) | 401 | 1.047
Q3 (2025) | 404 | 1.0548
Q4 (2025) | 407 | 1.0627
Q1 (2026) | 410 | 1.0705
Q2 (2026) | 414 | 1.0809
Q3 (2026) | 417 | 1.0888
Q4 (2026) | 419 | 1.094
Q1 (2027) | 422 | 1.1018
Q2 (2027) | 425 | 1.1097
Q3 (2027) | 426 | 1.1123
Q4 (2027) | 429 | 1.1201
Q1 (2028) | 433 | 1.1305
Q2 (2028) | 434 | 1.1332
Q3 (2028) | 437 | 1.141
Q4 (2028) | 441 | 1.1514
Q1 (2029) | 445 | 1.1619
Q2 (2029) | 447 | 1.1671
Q3 (2029) | 449 | 1.1723
Q4 (2029) | 453 | 1.1828
Q1 (2030) | 455 | 1.188
Q2 (2030) | 459 | 1.1984
Q3 (2030) | 461 | 1.2037
Q4 (2030) | 464 | 1.2115
Q1 (2031) | 469 | 1.2245
Q2 (2031) | 478 | 1.248