## Outputs
No. of prisoners | 1440 | Input figure here
Required GIFA | 56706
Calculated Total GIFA ÷ Millsike Density
No. of Houseblocks req'd | 6
Calculated Total GIFA ÷ Millsike Density
Buildings | GIFA
ERH (core) | 3059
ERH (offices) | 200
ERH (visits hall) | 1400
Support | 770
Central services (core) | 3130
Central services (education) | 1500
Central services (gym) | 300
Kitchen | 1926
Workshop | 7257
CASU | 648
Houseblock | 30430
OPU | 6086
Required Acres | 51.0618
Calculated Total GIFA ÷ Millsike Density
Programme (wks) | 154
Houseblock Duration + ((Number of Blocks - 1) × 4 Weeks) + Commissioning
Description | Cost / m2
Profit | 6767861.1
Central OH | 17789806.32
Site OH A | 24870684.54
Site OH B | 28036580.52
Risk | 8128238.04
Specialist fees | 1781135.46
Precon fees | 1201033.08
Regulatory fees | 0
Demo | 0
Substructure | 22442533.62
Superstructure Env | 80536129.44
Superstructure Sub | 21404246.76
Finishes | 18586525.62
Fittings | 6128784.48
M&E | 127511379.84
External works | 95928406.08
Minor works | 6738941.04
TOTAL | 467852285.94

## Background
Prisoners (Total) | 1440
Prisoners (per HB) | 240
GIFA | 56706
Site area | 143.5
Area / prisoner | 39.3792
Programme (HBs) | 122
Programme (Stagger) | 4
Programme (Commissioning) | 12
Building | GIFA | Status | m2 / person | Notes
ERH (core) | 3059 | Fixed
ERH (offices) | 200 |  | 0.13889
ERH (visits hall) | 1400 |  | 0.97222
Support | 770 | Fixed
Central services (core) | 3130 | Fixed
Central services (education) | 1500 |  | 1.0417
Central services (gym) | 300 |  | 0.20833
Kitchen | 1926 | Fixed
Workshop | 7257 |  | 1200 | per additional HB
CASU | 648 | Fixed |  | 1 additional CASU per 6 HBs
Houseblock | 6086 | Fixed
OPU | 6086 | Fixed |  | 1 additional OPU per 6 HBs
Description | Cost / m2
Profit | 119.35
Central OH | 313.72
Site OH A | 438.59
Site OH B | 494.42
Risk | 143.34
Specialist fees | 31.41
Precon fees | 21.18
Regulatory fees
Demo
Substructure | 395.77
Superstructure Env | 1420.24
Superstructure Sub | 377.46
Finishes | 327.77
Fittings | 108.08
M&E | 2248.64
External works | 1691.68
Minor works | 118.84